## Sheet1
Story ID | Story Name | Description | Priority | Iteration number | Acceptance Criteria | Notes | Date started | Date finished
1 | types of account | As a user, I want to be able to open more than one type of account with different service respectively, so that I can manage my finance in various way | 1 | 1 | Verify that we use inheritance to create mutiple-type accounts; Verify that we can use private to protect the security of class. Verify that we have three cases below: 1. Saver account 2. Junior account 3. Current account So u have 3 different classes extending bankaccount.class | 5.21 | 5.22
2 | confirm status | As a bank, I wan to confirm the status of customers, so that I can determine the next step. | 2 | 3 | Verify that we use the XML attribute to express the status of accounts. Verify that we need to check the status before each operation. | 5.24 | 5.25
3 | open account | As a user, I want to be able to provide enough information, including satisfactory credit history or something, so that I can get a unique account | 2 | 2 | Verify that we learn the basic information as class variation of master class; Verify that each object need a unqiure account number; | 5.22 | 5.23
4 | deposit funds | As a user, I want to deposit in an account providing the appropriate account number, so that I can manage my finance only by myself precisely. | 2 | 2 | Verify that customers use the PIN to deposit funds; Verify that bank check the funds whether it is cleared; | 5.22 | 5.24
5 | clear funds | As a bank, I want to be able to clear un-cleared funds periodically, so that bank can credit to the account. | 2 | 2 | Verify that the bank can periodically clears un-cleared funds. | 5.22 | 5.24
6 | withdraw funds | As a bank, I want to be provided with account number, an appropriate identification, and the amount to be withdrawn, so that bank can give funds to the customers in security | 2 | 2 | Verify that customers can withdraw funds supplying ac_number; Verify that only the current account can be withdrawed additional funds with overdraft limit; Verify that a minimum period of notice must be given before any withdrawal can be made in a saver account; | 5.22 | 5.23
7 | suspend account | As a bank, I want to be able to suspend an account, so that I can manage the customers' accounts formally. | 2 | 2 | Verify that the bank can suspend accounts. Verify that the bank need to check the accounts before each behavior. Verify that an attribute need to be marked in the .xml files | 5.22 | 5.23
8 | close account | As a user, I want to be able to close my accounts, so that I can clear useless accounts. | 2 | 2 | Verify that customers can choose to close accounts of them. | 5.22 | 5.23
9 | Interaction | As a user, I want to manage the bank with friendly help, so that I can process the transactions quickly. | 3 | 3 | Verify that the cmd interaction design. Verify that the interaction is friendly and we can modify what we input wrongly. | 5.24 | 5.25